## Slide 1: NEC 3 Part 1
By Trevor Drury

## Slide 2: Programme
Day 1
NEC 3 – Option A Priced contract with activity schedule
Main core clauses overview :
  Contractor and PM responsibilities, time, testing & defects, stage payments, activity schedules, Early Warning Notices, risk review meetings and risk registers, compensation events, quotations, termination
Change Overview : notices, timing – group work exercise
Timescales for Compensation events – group work exercise Compensation events, changes to prices – group work exercise session
Programme – the accepted programme, revision/update, evaluating extensions of time, ownership of float
Questions
Homework question paper handed out for completion by Day 2
Notes: All of us are project managers in our day to day lives in one way or another however, construction projects are complex and frequently involve large sums of money. Therefore, the profession of project management has evolved in recent years.
The role of the PM was once undertaken by the Architect but as projects have become more and more complex with faster delivery times there was a need for a specialised manager of the construction process

## Slide 3: Programme
Day 2
  Review of question paper from Day 1, answers and discussion of issues raised
  The NEC Short Form of Contract and how it differs from the main NEC 3
  Invitations to tender (ITT)
  Works information
  Contract data parts 1 and 2
  Secondary & Option Clauses W, X, Y and Z clauses
  Schedule of cost components
  Dispute resolution
  Payment and the Construction Act and group worked exercise
  NEC – signed underhand or by deed ( limitation period issues)
  Changes in the latest NEC 3 April 2013 edition (BIM, Project Bank Accounts etc.)
  Questions

## Slide 4: Core Clauses
General:
  The Employer, the Contractor, the Project Manager and the Supervisor shall act as stated in this contract and in a spirit of mutual trust and c0-operation (10.1)
  Terms that are identified in the Contract Data are in italics e.g. “Employer”
  Defined Terms have CAPITAL initials e.g. “Completion Date”

## Slide 5: Core Clauses - Identified and Defined Terms
The Accepted Programme:
  The programme in the Contract Data or the latest accepted by the PM
Completion is when the Contractor has:
  Completed all work which the Works Information states that he is to do by the Completion Date and corrected notified Defects which would have prevented the Employer and others from using the works

## Slide 6: Core Clauses - Identified and Defined Terms
Defects Certificate: a list of defects issued by the Supervisor before the defects date and uncorrected. If no defects, a statement that there are none
The Risk Register is a register of risks listed in the Contract Data and risks identified by the PM or the Contractor as an early warning . It must include a description of the risk and actions to be taken

## Slide 7: Core Clauses - Identified and Defined Terms
Works information is: information which specifies and describes the works or states any constraints on the Contractor. This is contained within the Contract Data or instruction
Defined Cost : cost of components in the Shorter Schedule of Cost Components

## Slide 8: Core Clauses - Identified and Defined Terms
The Price for Work Done:
  Total of Prices for each group of completed activities and each completed activity not in a group
  Prices are lump sum prices for each of the activities on the Activity Schedule unless changed in accordance with the contract i.e. by an instruction

## Slide 9: Core Clauses - Communications
Must be in a form that can be read, copied and recorded
Has effect when received at last address notified/address stated in Contract Data
Reply within the period for reply ( as set out in Contract Data)
If PM does not accept a Contractors communication, PM must give reasons and Contractor must resubmit. One such reason can be more information is needed from the Contractor. This is not a Compensation Event

## Slide 10: Core Clauses – PM & Supervisor
Acceptance of a communication from the Contractor or of his work does not change the Contractors responsibilities or liability
PM or Supervisor can delegate actions
PM can instruct changes to the Works Information or a Key Date

## Slide 11: Core Clauses – Early Warning
Cl. 16.1 Both Contractor & PM give an Early Warning to the other as soon as either becomes aware of any matter which could:
  Increase the total of the Prices
  Delay Completion
  Delay a Key Date
  Impair performance of the works in use

## Slide 12: Core Clauses – Early Warning
Contractor may give an EWN to the PM of any matter that could increase his total cost!!!
PM enters early warning matters into the Risk Register
PM or Contractor may notify the other to attend a risk reduction meeting

## Slide 13: Core Clauses – Early Warning Risk Reduction Meeting
Consider proposals for reducing or avoiding the registered risk
Seek solutions to bring advantage to all affected
Decide actions and who, as per the contract will take them
Decide which risks have been avoided or have passed and can be removed from the register
PM revises Risk Register and issues revision
May require an Instruction which is issued simultaneously

## Slide 14: What should a Risk Register Contain?
Description of the risk
% likelihood
Consequences: Time impact – Low, Medium, High
The owner of the risk
Cost risk allowance in total of Prices i.e. What is included in the contract
Cost reduction allowances for events outside Prices managed by the Client as a contingency
Predicted risk expiry date
Actual risk expiry date
Actions to avoid or reduce risk
Comments

## Slide 15: For Next Workshop!
Review your own Risk Register template. Does it include all of the columns and information above?
Everyone to review a risk register and understand how it works and why it is important
Bring with you for next time a copy of a real risk register that you have created or are using on a project.

## Slide 16: Early Warning & Change Process
Potential Event
Early Warning notice
(Clause a)
Risk Reduction meeting
(Clause b)
No change to Completion Date or Prices
No CE
No change to Completion Date or Prices when event due to fault of Contractor or if there is no time or cost effect
(Clause c)
PM gives instruction to submit quotation as to time and cost consequences
(Clause d)
Is a CE
Quotation submitted by Contractor within 3 weeks
(Clause e)
Quotation Accepted by PM within 2 weeks
(Clause f)
Is a CE

## Slide 17: Early Warning & Change Process
Potential Event
Early Warning notice
16.1
Risk Reduction meeting
16.3
No change to Completion Date or Prices
No CE
No change to Completion Date or Prices when event due to fault of Contractor or if there is no time or cost effect
61.4
PM gives instruction to submit quotation as to time and cost
61.1
Is a CE
Quotation submitted by Contractor within 3 weeks
62.3
Quotation Accepted by PM within 2 weeks
62.3
Is a CE

## Slide 18: Core Clauses – Contractor’s Responsibilities
Contractor provides Works in accordance with the Works Information. As the Contractor’s price is tendered on this information it therefore needs to meet the clients needs/requirements!!
Contractor may design all or parts of the Works.
Contractor does not proceed unless PM has accepted its design.
Grounds for not accepting – not in accordance with Works information or applicable law
A requirement to co-operate with Others in receiving/providing information

## Slide 19: Core Clauses – Contractor’s Responsibilities
Any costs incurred by Employer where Contractor fails to provide services etc. set out in Works Information is assessed by PM and paid for by the Contractor.
If PM decides work does not meet Condition by a Key date and the Employer incurs additional cost, PM assesses cost within 4 weeks and is paid for by Contractor.
Contractor submits proposed sub-contract conditions to PM for acceptance unless an NEC form is used or PM agrees that no submission required
Must accept Instructions from PM and Supervisor

## Slide 20: Core Clauses – Time
If Programme not contained in Contract Data, Contractor to submit to PM for acceptance within period stated (31.1)
Every programme must have all of the information set out in clause 31.2. Note that it must include float, time risk allowances & H&S requirements
Method statement – how each operation is to be undertaken , plant(equipment) and other resources to be used
Advice! – request electronically with full network analysis. You may also wish to specify the software to be used e.g. Primavera P6 or Asta Power project

## Slide 21: Core Clauses – Time
Timing
  Within 2 weeks PM must accept or reject programme giving reasons for non-acceptance (31.3)
  Reasons limited to:
    Contractor’s plans not practicable
    Does not show information required by contract
    Unrealistic
    Does not comply with the Works Information

## Slide 22: Core Clauses – Time
For Option A
  The Contractor is required to provide information that shows how each activity on the ACTIVITY SCHEDULE relates to the activities/operations on the accepted programme (31.4)
  A revised programme must be submitted by the Contractor for acceptance (32.2):
    Within the period for reply after being instructed to
    Within the interval stated in the Contract Data

## Slide 23: Core Clauses – Time
The Revised Programme (32.1) must show:
  Actual progress and effect on subsequent work
  The effect of implemented CE’s and EW’s
  How the Contractor plans to overcome delays remedy defects
  Other Contractor proposed changes to Accepted Programme

## Slide 24: Core Clauses – Time
Take over:
  Employer does not have to take over the works before the Completion Date if stated in Contract Data
  Takeover – up to 2 weeks after Completion (35.1)
  Employer may use any part of the works before Completion certified however; that part is deemed to have been taken over unless:
    For reason set out in Works Information
    To suit the Contractor’s method of working

## Slide 25: Core Clauses – Time
Acceleration (36):
  PM may instruct a quotation stating Key Dates to be included
  Quotation must include changes to Prices and a revised programme showing the earlier Completion Date and changed Key Dates
  When PM accepts such a quotation he accepts changes to prices , Completion Date and Key Dates and accepts the revised programme

## Slide 26: Core Clauses – Testing & Defects
Supervisor:
  Must not cause unnecessary delay to work or payment conditional upon test results (40.5)
  PM assesses cost of any re-tests which is to be paid for by the Contractor (40.6)
  Up to the defects date Supervisor can instruct Contractor to search for a defect giving reasons (42.1)
  Until the defects date Supervisor notifies Contractor of each defect as soon as identified and the Contractor vice versa (42.2)

## Slide 27: Core Clauses – Testing & Defects
Correcting defects:
  Contractor to do so whether notified or not
  Contractor corrects a notified defect before end of defect correction period . This begins at Completion, for Defects notified before Completion and when the Defect is notified for other Defects. (43.2)

## Slide 28: Core Clauses – Testing & Defects
Supervisor issues Defects Certificate at defects date or defects correction period, which ever is the later (43.3)
Access arranged by PM for correction of defects after take over
Defects can be accepted and Works Information amended (44.1)
Contractor submits quotation to reduce Prices and Completion for PM acceptance (44.2)
Contractor pays for uncorrected defects (45.1/45.2)

## Slide 29: Core Clauses – Payments
PM assesses amount due including VAT and considers any application submitted by Contractor
25% withheld if Contractor fails to submit first programme (50.3)
PM certificate within 1 week of assessment date (51.1)
Payment within 3 weeks of assessment date(51.2)
Contractor’s costs not included in the Defined Cost are deemed included in the fee

## Slide 30: Core Clauses – Payments
Activity Schedule:
  Information contained therein is not Works Information or site Information – it is purely for payment purposes
  Must be updated if Contractor changes method/programme for acceptance by PM (54.2)
  PM may not accept revision :
    If it does not accord with the Accepted Programme
    Prices are not reasonably distributed – Cash flow /over payment issue
    Total price has changed

## Slide 31: Core Clauses – Payments
Set out in clause 60 – 19 events listed
Covers:
  PM instructions changing Works Information
  Access issues
  Late information
  Instruction to stop or not to start work
  Failure to respond to a communication
  Instruction to deal with object of value /historic/interest
  PM changes a previous decision
  PM withholds acceptance of a quotation for reasons not in accordance with contract

## Slide 32: Core Clauses – Compensation Events
Covers (cont’d)
  Supervisor causes delay
  Contractor encounters physical conditions that could not have been foreseen or chances of occurrence very small
  Adverse weather compared to last 10 years

## Slide 33: Core Clauses – Compensation Events
Notification:
  PM/Supervisor instruction – PM notifies Contractor at the time of giving the Instruction. He requests quotations unless Contractor at fault (61.1)
  PM may instruct Contractor for a quotation for a proposed instruction or changed decision – has no effect until accepted
  Contractor notifies PM of an event that has happened or expects to happen
  Contractor must notify within 8 weeks. Over 8 weeks loss of right to recover change in Prices and Completion Date/Key Date unless PM should have notified (61.3)

## Slide 34: Core Clauses – Compensation Events
Completion Date and Prices are not changed if PM considers event due to Contractor, has not happened/not expected to happen, has no effect or is not a compensation event stated in the contract.
If PM fails to respond within 1 week ( or otherwise agreed), Contractor may notify to that effect. PM has a further 2 weeks of this notice to reply otherwise it is considered acceptance by PM a Compensation Event and an instruction to submit a quotation (61.4)

## Slide 35: Core Clauses – Compensation Events
Quotations:
  PM may instruct alternative quotations (62.1)
  Quotations include changes to Prices, delay to Completion Date and Key Dates. Full details to be provided of its assessment including alterations to the Accepted Programme (62.2)
  Contractor has 3 weeks to submit. PM has 2 weeks to reply (62.3)
  If PM instructs Contractor for a revised quotation, Contractor has a further 3weeks (62.4)

## Slide 36: Core Clauses – Compensation Events
If PM fails to respond to quotation(s) within time, Contractor gives notice and PM has 2 weeks to reply. Failure to do so enables Contractor to treat quotation as accepted. (62.6)

## Slide 37: Core Clauses – Assessing Compensation Events
Prices are assessed as to the effect of the compensation event on (63.1):
  the Defined Cost of work done
  the forecast Defined Cost no yet done
  the resulting fee
If PM notifies Contractor that he did not give an Early Warning of a compensation event, the event is assessed as if the Contractor did (63.5)

## Slide 38: Core Clauses – Assessing Compensation Events
The effect of a compensation event may reduce the total Defined Cost (63.10)
Assessments for changes to Prices for compensation events are in the form of changes to the Activity Schedule (63.12)
If agreed, rates and lump sums can be used to assess compensation events (63.14)

## Slide 39: Core Clauses – Project Manager’s Assessments
When (64):
  Contractor has not submitted a quote & details
  If Contractor has not assessed correctly
  If the Contractor fails to submit a programme
  When there is no Accepted Programme PM makes his own assessment
  If PM fails to assess a compensation event within time, Contractor notifies, PM has another 2 weeks. If still no reply, Contractors quote deemed accepted

## Slide 40: Core Clauses – Compensation Events
Compensation event becomes implemented when (65.1):
  PM notifies acceptance of quote
  PM notifies of his own assessment
  Contractor’s quotation deemed accepted by PM
  The Changes to Prices, Completion Date and Key Dates are included in the notification of a compensation event.
  NB: There is no EOT or Loss and Expense provision beyond Compensation Events

## Slide 41: Compensation Events
Potential
Compensation Event
C Notifies
PM
PM instructs C to give Quotation(s)
Time?
C submits quotations(s)
PM’s
response
Acceptance
Decision not to proceed
Time?
Time?
Clause?
Clause?
C submits revised quotations(s)
Time?
PM’s to make
Own assessment
C informed of
PM assessment
Clause?
Clause?
Clause?
2 weeks
Clause?
2 weeks

## Slide 42: Compensation Events
Potential
Compensation Event
C Notifies
PM
PM instructs C to give Quotation(s)
1 week
C submits quotations(s)
PM’s
response
Is a CE
Acceptance
Decision not to proceed
3 weeks
8 weeks
61.4
61.3
C submits revised quotations(s)
3 weeks
PM’s to make
Own assessment
C informed of
PM assessment
62.3
62.4
62.3
2 weeks
62.3
2 weeks

## Slide 43
If you have any questions please contact
trevor.drury@morecraft-drury.com
Morecraft Drury
Central Court
25 Southampton Buildings
London WC2A 1AL
www.morecraft-drury.com
Thank You