## Slide 1: NEC 3 - Part 2
By Trevor Drury

## Slide 2: Programme
Day 1
NEC 3 – Option A Priced contract with activity schedule
Main core clauses overview :
  Contractor and PM responsibilities, time, testing & defects, stage payments, activity schedules, Early Warning Notices, risk review meetings and risk registers, compensation events, quotations, termination
Change Overview : notices, timing – group work exercise
Timescales for Compensation events – group work exercise Compensation events, changes to prices – group work exercise session
Programme – the accepted programme, revision/update, evaluating extensions of time, ownership of float
Questions
Homework question paper handed out for completion by Day 2
Notes: All of us are project managers in our day to day lives in one way or another however, construction projects are complex and frequently involve large sums of money. Therefore, the profession of project management has evolved in recent years.
The role of the PM was once undertaken by the Architect but as projects have become more and more complex with faster delivery times there was a need for a specialised manager of the construction process

## Slide 3: Programme
Day 2
  Review of question paper from Day 1, answers and discussion of issues raised
  The NEC Short Form of Contract and how it differs from the main NEC 3
  Invitations to tender (ITT)
  Works information
  Contract data parts 1 and 2
  Secondary & Option Clauses W, X, Y and Z clauses
  Schedule of cost components
  Dispute resolution
  Payment and the Construction Act and group worked exercise
  NEC – signed underhand or by deed ( limitation period issues)
  Changes in the latest NEC 3 April 2013 edition (BIM, Project Bank Accounts etc.)
  Questions

## Slide 4: Works Information
Good Works information reduces misunderstanding and disputes.
Works information is defined at 11.2 (19)
It should be “ a complete and precise statement of the Employer’s requirements. If it is not, there is a risk that the Contractor will interpret it differently from the Employer’s intention”
Works information is provided by the Employer and the Contractor. Both are separated

## Slide 5: Works Information
Employer’s Works information includes:
  Technical information, specifications and drawings
  Constraints
  Requirements for work to be designed by the Contract
Contractor’s Works information is particulars of the Contractor’s design
Contractor’s primary obligation is to provide the Works in accordance with the Works Information (20.1) and hence why it is important to get it right

## Slide 6: Works Information
The Contract Data sets out where the Works Information is to be found
Works information should not repeat, contradict or create an ambiguity with the Contract Data or Conditions of Contract
Works Information is different to Site Information – Site Information describes the site before commencement and Works Information describes what is to be done on the site.
Works Information and Site Information is incorporated into the Contract by reference to documents listed in the Contract Data.

## Slide 7: Works Information
Site Information includes:
  Subsoil investigations
  Reports obtained by Employer e.g. Hydrographic data
  Reference to publicly available documents concerning the site
  Charted services
  Information about buildings ,structures and machinery
Distinction between Works Information & pricing documents
  Pricing information explains prices and does not describe the Works
  Pricing documents do not change the Contractor’s obligations to provide the Works in accordance with the Works Information

## Slide 8: Works Information
Unlike some contracts there is no hierarchy of documents save that the Works Information has priority over the Contractors information
Ambiguities are to be dealt with by the PM under 17.1 by the issue of an Instruction
This leads to a Compensation Event under 60.1 (1) unless as a result of the Contractor changing his design to comply with the Works Information
Ambiguities in the Site Information is resolved in favour of the Contractor

## Slide 9: Works Information
Must be clear, complete and precise.
Standard specifications should be reviewed and amended before incorporation and great care should be taken. Many claims have arisen out of cutting and pasting specifications from previous jobs!
Specifications should be checked for consistency with other contract documents
Avoid subjective requirements such as “in the opinion of”

## Slide 10: Works Information
Keep it simple – clarity and simplicity are required
Use simple words
Sentences should be as short as possible
Use bullet points for lists
Unlike many contracts NEC 3 uses few adjectives or adverbs and is possibly the most important drafting convention in NEC .
Capitals – used for defined terms

## Slide 11: Works Information
Chapter 4 of the NEC Works Information Guidance sets out each clause / sub-clause where Works Information is referred to and what should be included
Works Information by the Contractor:
  Where design is submitted for acceptance, the Works information will change over time
  Warning ! Where the Contractor has offered an alternative proposal to the Employer’s Works Information, if accepted, the Employer’s Works Information must be changed

## Slide 12: Contract Data
Data provided by the Employer – Part 1
  General – select one main option (Option A) and a dispute resolution option( W2 if HGCRA applies). In addition select the secondary option clauses appropriate
  State who the Employer is and its usual address. Does not have to be the registered address
  The name and address of the PM. It is important that the chosen PM has the time to carry out his duties effectively and the Employer’s authority to act.
  The Supervisor’s name and address – important role in checking works are in accordance with drawings and specifications and issues the Defects Certificate

## Slide 13: Contract Data
  The Adjudicators name and address e.g. Trevor Drury .... or name the Nominating Body.
  State in which documents the Works Information is contained. The guidance note refers to parts 2,3 and 4 of the enquiry document and similarly part 5 for Site Information
  Site boundaries need to be stated which is usually in the form of a drawing which is referred to here in the Contract Data
  Time – starting date of contract and access dates need to be entered
  Enter the defects date and the period(s) for defects correction
  Payment –enter payment interval and interest rate for late payment
  Weather – where is it to be recorded

## Slide 14: Contract Data
Weather – days of snow lying before a compensation event due, who is to supply the weather data and where is it to be recorded. Where no weather records available, assumed values are entered.
Insurances – limits of indemnity

## Slide 15: Contract Data
Optional statements cover:
  Tribunal – arbitration? Procedure? Name of arbitrator or nominating body
  Completion date, is Employer unwilling to Take Over early?, if no programme requirement in part 2 , when is the Contractor to submit its first programme
  Key Dates
  Payment period if not 14 days
  Any additional compensation events
  Any additional Employer’s risks - for risks that may be unfair to pass down to Contractor
  Insurance for any Employer plant
  Insurances to be provided by Employer and level of indemnity

## Slide 16: Contract Data
Options X1 to X20
Z clauses
Part 2 to be provided by the Contractor
Name and address
Direct fee %
Subcontracted fee %
Working areas
Key personnel
Items to be included in the Risk Register

## Slide 17: Contract Data
Optional Statements
  Where Works Information is contained relating to the Contractor’s design
  Programme details
  Completion date for the whole works
  Activity Schedule location
  Tendered total of Prices
  % for people overheads ( prelims)
  Equipment lists and % addition/reduction
  Rates for other equipment
  Hourly rates for Defined cost of design
  % for design overheads
  Expenses for design employees included in Defined Cost

## Slide 18: Assessing Compensation Events
Clause 63.1 The Changes to the Prices are assessed as the effect on:
  The Actual Defined Cost already done
  The Forecast Defined Cost for work not yet done
  The resulting fee
Defined Cost is stated at 11.2 (22) – “Defined Cost is the cost of components in the Shorter Schedule of Cost Components whether work is subcontracted or not excluding the cost of preparing quotations for compensation events

## Slide 19: Assessing Compensation Events
The Schedule of Cost Components – see P41 & 42
Lists 7 criteria:
  People
  Equipment
  Plant & Materials
  Charges
  Manufacture & Fabrication
  Design
  Insurance

## Slide 20: Assessing Compensation Events
E.g. People costs i.e. those costs paid by the Contractor plus those costs of employment required by law and pension, for those directly employed and normally working within the Working Area
Determine what costs fit by reference to the Data for Shorter Schedule of Cost Components contained within Contract Data Pt. 2. – see P 52
The percentages stated are applied to give the component cost or the Defined Cost of People
The fee is as stated in 11.2.(8)

## Slide 21: Secondary Options
X1 to X20
X1 price adjustment for inflation– to be used in periods of high inflation and long term projects
X4 Parent Company Guarantee – in the form provided in the Works Information
X5 Sectional Completion – clarity required stating what is included in each section
X7 Delay Damages – the rate is stated in the Contract Data at a daily rate. Must be a genuine estimate of the Employer’s loss and not a penalty

## Slide 22: Secondary Options
X12 Partnering - Core Group, Partnering Information, KPI’s & incentives
X13 Performance Bond – in the form and in the amount stated in the Works Information. Must be within 4 weeks of contract date. “On demand” or surety bond
X15 Limitation of the Contractor’s Liability for his design to reasonable skill and care
X16 Retention
X18 Limitation of Liability – a cap on indirect or consequential loss. Also covers liability for defects, delay damages and so on.

## Slide 23: Secondary Options
Y (UK) 2 – HGCRA 1996 as amended by the LDEDC Act 2009
Z Clauses
  There are a set of standard clauses for use by Government agencies

## Slide 24: Payment – Compliance with Construction Act
Since 1999 the construction industry has been subject to the Housing, Grants, Construction and Regeneration Act 1996 which has been amended by the Local Democracy, Economic Development and Construction Act 2009
The amendments took effect on 1 October 2011

## Slide 25: Payment – Compliance with Construction Act
The effect of changes to the NEC3
108(3A) – contract must include in writing a provision for the correction of slips
108A – Any provision seeking to restrict the Adjudicator’s power to allocate his fees is to be ineffective
110A – substantial amendments to payment provisions. Where payment follows the issue of a payment certificate, the certificate and details of how the payment has been calculated must be issued together as the “payment notice”

## Slide 26: Payment – Compliance with Construction Act
The notice must be issued within 5 days of the payment due date
111 – replaces the requirement to issue a notice to withhold payment with the requirement to pay the notified sum or give notice to pay less
111 (9) – a new provision requiring that payment must be made within 7 days of an Adjudicator’s decision which increases the amount due under a payment notice
Option W2 is amended to change 14 days to 5 days
112 – contractors right to recover costs of suspension

## Slide 27: Payment – Compliance with Construction Act
Amendments to the NEC3
  Page 55 Option Y (UK) 2 : Y2.2 – 3rd paragraph replaced with:
  “ The Project Manager’s certificate is the notice of payment to the Contractor specifying the amount due at the payment due date (notified sum) and stating the basis on which the amount was calculated”

## Slide 28: Payment – Compliance with Construction Act
Y2.3 replaced with the following:
  “ If either Party intends to pay less than the notified sum, he notifies the other Party not later than seven days (the prescribed period) before the final date for payment by stating the amount considered to be due and the basis on which that sum is calculated. A Party does not withhold payment of an amount due under this contract unless he has notified his intention to pay less than the notified sum as required by this contract”

## Slide 29: June 2013
 | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Week 1 |  | 1 | 2 | 3 | 4 | 5 | 6
Week 2 | 7 | 8 | 9 | 10 | 11 | 12 | 13
Week 3 | 14 | 15 | 16 | 17 | 18 | 19 | 20
Week 4 | 21 | 22 | 23 | 24 | 25 | 26 | 27
Week 5 | 28 | 29 | 30 |  |  |  | 
Payment due 7 days after assessment date
Certificate to be issued and details of how amount calculated no later than 5 days after due date
Last date for issue of Certificate
Due Date
Assessment Date
Notice to Pay Less 7 days back from final date
Latest Date for Payment 14 days from Due Date etc

## Slide 30: Payment – Compliance with Construction Act
If the assessment date is the 14th June 2013:
When does the Certificate and supporting calculations have to be issued ?( no of days and date)
What is the Due Date for Payment?
What is the Final Date for Payment?
What is the latest date for issue of a Notice to Pay Less?

## Slide 31: Payment – Compliance with Construction Act
If the assessment date is the 14th June 2013:
When does the Certificate and supporting calculations have to be issued ? – 5 Days after the Due Date – 26 June
What is the Due Date for Payment? – 21 June
What is the Final Date for Payment? – 5 July
What is the latest date for issue of a Notice to Pay Less? – 28 June

## Slide 32: Short Contract
For projects not requiring sophisticated management
For straight forward work – value not the issue
Of low risk to both parties
Employer uses package to invite tenders
  Title page, contract data, Contractor’s offer, Employer’s acceptance and Price List

## Slide 33: Short Contract
Information provided by Contractor only listed in Works Information only if Employer satisfied that it is required
Works Information important as defects based on what is stated in the Works Information
Employer may include a list of subcontractors to select from
Employer sets out constraints such as requirement to work with other activities/contracts and any Employer’s work that will impact on the Contractor
State whether a programme is required and in what form
Provide list of Adjudicators for Contractor to select 1

## Slide 34: Short Contract
Other differences with main NEC form:
  Contract data is at the front of the document and with Works Information, Contractors Prices etc. makes the Contractor’s offer and is signed by the Employer , if accepted , to form the contract
  No access dates
  No PM or Supervisor
  No compensation event information for weather
  Nothing mentioned regarding Take – Over
  There is a Price List page which builds up the Contractor’s price and is flexible in that it can form a schedule of rates with quantities or lump sums

## Slide 35: Short Contract
Works Information
  Description
  Drawings
  Specifications
  Constraints
  Requirements for Programme
  Services & other things provided by Employer
  Site Information

## Slide 36: Short Programme
Employer administers contract but can delegate to others
Risk – No risk register mentioned in contract or formal risk meetings however; Contractor and Employer to cooperate to avoid or reduce effects of risk
Employer has to accept design of Contractor before Contractor allowed to start
No provision for inflation
No provision for advance payments

## Slide 37: Short Contract
Payment
  Contractor submits application by assessment date
  Employer corrects any errors
  Issues a notification
  Retention taken
  25% retained for failure to provide first programme
  Employer pays within 3 weeks after next assessment day (51.1)

## Slide 38: Short Contract
Compensation events
  Contractor takes risk of weather up to a cap (one seventh)
  Quotations within 2 weeks
  Employer replies within 2 weeks

## Slide 39: Dispute Resolution
Referred to an adjudicator
Must notify of a dispute within 4 weeks of being aware of it
If a further 2-4 weeks have passed, a party can refer to adjudication
Failure to comply with the above – parties are time barred
Adjudicator’s decision within 4 weeks

## Slide 40: Dispute Resolution
Parties carry on as if matter had not been referred to adjudication
Decision binding until finally determined by the tribunal
Arbitration only after adjudication
Has to notify other party within 4 weeks of Adjudicator’s decision

## Slide 41: Changes in the NEC 3 2013 Version
The main changes are:
  Updated with amendments e.g. Changes to Construction Act
  Introduction of Project Bank Accounts
  Requirement for Contractor to submit applications for payment
  Some changes to 61.1, 61.3, 61.4
  Updated to incorporate BIM

## Slide 42: Executing the Contract
No where to sign in the main form!
Letter bringing contract together – “under hand” 6 years limitation of liability
If 12 year limitation period is required, a deed will be necessary. This will need to be a separately drafted agreement which should also list all of the documents that form the agreement between the parties

## Slide 43
If you have any questions please contact
trevor.drury@morecraft-drury.com
Morecraft Drury
Central Court
25 Southampton Buildings
London WC2A 1AL
www.morecraft-drury.com
Thank You