## Slide 1: Project Management the Risks!
By Trevor Drury
© Morecraft Drury 2014

## Slide 2: What is Project Management?
All of us are project managers in our day to day lives in one way or another however, construction projects are complex and frequently involve large sums of money.
Therefore, the profession of project management has evolved in recent years.
The role of the PM was once undertaken by the Architect but as projects have become more and more complex with faster delivery times there was a need for a specialised manager of the construction process.
© Morecraft Drury 2014
Notes: All of us are project managers in our day to day lives in one way or another however, construction projects are complex and frequently involve large sums of money. Therefore, the profession of project management has evolved in recent years.
The role of the PM was once undertaken by the Architect but as projects have become more and more complex with faster delivery times there was a need for a specialised manager of the construction process

## Slide 3: What is Project Management?
Unfortunately the title “project manager” means different things to different people. Often the contractor gives his site based agent the title “project manager” yet the client also gives this title to his representative. It is the latter we are concerned with .
The other issue is whether the role is full project management or is it project co-ordination?
Project co-ordination is usually for a part of the development process. If the PM appoints consultants it is usually deemed “project management”, if the client appoints the consultants, “project co-ordination”
© Morecraft Drury 2014

## Slide 4: What is Project Management?
There are a number of services that can be added to the basic project management service this is why it is important to ensure the project management firm has a contract in writing that sets out exactly the service that is to be provided. Invariably this is not adequately set down or those fulfilling the day to day role do not fully understand their obligations.
The Chartered Institute of Building has a Code of Practice that lists those services that are suggested plus possible additional duties. RICS also provides guidance in Appointing a Project Manager.
The flexibility of what may or may not be included is part of the problem for project managers and their insurers. The courts have also implied what duties a competent PM should undertake.
© Morecraft Drury 2014

## Slide 5: RICS – “Appointing a project manager”
Ist Edition April 2013
This is a Guidance Note as far as a Chartered Surveyor is concerned and is “Recommended Good Practice”
Members are not required to follow the recommendations but:
  “ When an allegation of professional negligence is made against a surveyor, a court or tribunal may take account of the contents of any relevant guidance notes published by RICS in deciding whether or not the member had acted with reasonable competence”
© Morecraft Drury 2014

## Slide 6: RICS Guidance
Definitions:
  “ a lead role in the development process with the responsibility for driving successful completion of the project and occupying the space between the employer and the building contract, design team, and other consultants employed on the project”
  The role often includes the management of the design and administration of the various design team appointments.
    Refer to RICS guidance notes Managing the design delivery and contract administration.
© Morecraft Drury 2014

## Slide 7: RICS Guidance
Distinguish between project/construction monitoring and development management although there may be overlaps with the latter
BS6079 part 2 definition:
  “ Planning, monitoring and control of all aspects of a project and the motivation of all those involved in it to achieve the project objectives on time and to the specified cost quality and performance.”
© Morecraft Drury 2014

## Slide 8: RICS Guidance
BS ISO 21500 (2012)
  “ The application of methods, tools, techniques and competences to a project. Project management includes the integration of the various phases of the project life cycle”
  CIOB Code of Practice
  An established discipline which executively manages the full development process, from the client’s idea to funding, co-ordination and acquirement of planning and statutory controls approval, sustainability, design delivery, through to the selection of procurement of the project team , construction, commissioning, handover, review, to facilities management co-ordination.”
© Morecraft Drury 2014

## Slide 9: RICS Guidance
Project Management is concerned with defining what has to be accomplished put simply as:
  Planning what needs to be done
  Implementing the plans
  Monitoring and controlling the project work
  Risk management
  The required processes should be set out in a Project Execution Plan
© Morecraft Drury 2014

## Slide 10: RICS GUIDANCE
Developments in recent years has introduced new terminology such as Portfolio and Programme Management:
Portfolio – total investment to bring about change in order to achieve strategic business objectives
Programme – groups of related but independent projects concerned with strategic benefits whereas portfolios are unrelated projects.
Project management – concentrates on defined outputs and one -off deliverables
© Morecraft Drury 2014

## Slide 11: RICS GUIDANCE
Surveyors must “act within the limits of their qualifications, knowledge and training and an appropriate qualification in project management, either educational or professional is recommended.
Where the PM also acts as Employer’s Agent, e.g. on D&B contracts, care must be exercised between the partisan role to the client and the requirement to act impartially in the administration of the contract. e.g. Issuing certificates, extensions of time etc.

## Slide 12: RICS GUIDANCE
RICS members are obliged to record the terms of their appointments in writing
Balance risk and liability between Client and PM
Care should be exercised when agreeing limits of liability and should be checked with PI Insurers

## Slide 13: RICS Guidance
A Project Management Agreement should include:
  Names of the parties
  Start and completion dates
  Applicable law
  Set out the basic and additional services
  General obligations and standards to be exercised
  Provision for instructions and changes
  H&S, statutory requirements, prohibitive materials
  Design responsibility
  Limitation on liability
  Collateral warranties/rights of 3rd parties

## Slide 14: RICS Guidance
Personnel
Client obligations
Payment – amounts/periods
Authority levels
Insurances
Copyright
Confidentiality
Assignment
Subcontracting
Suspension and termination
Dispute resolution
Notices
© Morecraft Drury 2014

## Slide 15: Typical Project Management Services
From CIOB Code of Practice for Project Management:
Assist preparing the project brief
Develop the project manager’s brief
Arrange for a feasibility study and report
Develop the project strategy
Prepare the Project Handbook
Develop the Consultants brief’s
Devise the project programme
© Morecraft Drury 2014

## Slide 16: Typical Project Management Services
Co-ordinate the design process
Appoint consultants
Arrange insurance and warranties
Select the procurement system
Arrange tender documentation
Pre-qualify contractors
Evaluate tenders
Participate in contractor selection
Participate in the contractor ‘s appointment
Organise control systems
Monitor progress
Arrange meetings
Authorise payments
© Morecraft Drury 2014

## Slide 17: Typical Project Management Services
Co-ordinate the design process
Organise communications /reporting system
Provide total co-ordination
Issue health and safety procedures
Address environmental aspects
Co-ordinate statutory authorities
Monitor budget and variation orders
Develop the final account
Arrange pre- commissioning and commissioning
Organise O&M manuals
© Morecraft Drury 2014

## Slide 18: Typical Project Management Services
Plan for the maintenance period
Develop the maintenance programme and staff training
Plan the facilities management
Arrange for feedback and monitoring
© Morecraft Drury 2014

## Slide 19: The Stages of Development
Inception
Feasibility
Strategy
Pre-construction
Construction
Services commissioning
Completion
Post completion review
© Morecraft Drury 2014

## Slide 20: Inception Stage
Development of the business case
Set the PM’s objectives and duties (development of PM’s brief)
Appointment of the PM to ensure professional, competent management co-ordination from the start. Examples of standard terms of engagement include: RICS Project Management Agreement, APM Terms of Appointment for a Project Manager, NEC Professional Services Contract, RIBA Form of Appointment for Project Managers and NHS Estates Agreement for the Appointment of Project Managers for commissions for construction projects in the NHS
© Morecraft Drury 2014

## Slide 21: Feasibility Stage
Outline project brief
Feasibility study reports including service and financial objectives, requirements and risks, public consultation, geo-technical study, environmental impact assessment, health and safety study, legal/statutory/planning requirements, estimates of capital and operating costs, assessment of potential funding and potential site assessments
Site selection and acquisition
Procurement route selection
© Morecraft Drury 2014

## Slide 22: Feasibility Stage
Detailed project brief
Scheme design
Funding and investment appraisal
Market suitability
Client decision to proceed
Project Execution Plan – developed by PM for the project sponsor and sets out the policies and procedures for the project , project scope, objectives and priorities. Used for sign off at the end of the feasibility and strategy phases, a prospectus for funding and information for prospective contractors. It contains plans, procedures and control processes for monitoring and reporting.
© Morecraft Drury 2014

## Slide 23: Strategy Stage
Selection of the project team
Reviewing and developing the project brief with the client
Develop organisation structure, roles and responsibilities
Communication routes
Decision points/Gateways
Compliance with CDM regulations
Application of value management
Advising client on appointment of additional consultants
Risk management procedures
Advising on most appropriate form of contract
© Morecraft Drury 2014

## Slide 24: Strategy Stage
Setting procedures for managing relationships, monitoring, control and administration of the project
IT
Project Master Schedule – it is the PM’s responsibility to monitor progress and identify risks and mitigation measures
Cost planning and development of the budget
Cost control – ensuring the project is within the approved budget, regular reporting and updating, management of change order process, provision of cash flows
Procurement – compliance with EU procurement directives etc.
Appointment of the project team
© Morecraft Drury 2014

## Slide 25: Strategy Stage
Management of all consultant activities – this is a very busy and important time with many design and procurement activities
Ensure statutory consents including necessary planning permission is in place, Building Regulations compliant
Bringing the contractor on-board
Pre-start meeting
Fee payment sign off to consultants
© Morecraft Drury 2014

## Slide 26: Pre-Construction Stage
Management of all consultant activities – this is a very busy and important time with many design and procurement activities
Ensure statutory consents including necessary planning permission is in place, Building Regulations compliant
Bringing the contractor on-board
Pre-start meeting
Fee payment sign off to consultants
© Morecraft Drury 2014

## Slide 27: Construction Stage
The “driver” of the project
Programme management
Budgetary control and checking payments
Managing change
Implementing corrective action where required
Management of the design team
Regular reporting to the client
Regular project meetings
Ensuring compliance with health and safety and CDM regs
© Morecraft Drury 2014

## Slide 28: Construction Stage
Ensure statutory and contractual formalities are in place before commencement on site including:
  Planning
  CDM notification
  3rd party insurance
  PI insurance of consultants
  Notice to start work issued to Local Authority
  Fire regulation compliance
  Performance bonds
On PC ensure electrical certificates, fire testing etc obtained
Regularly update risk register
Management of the supply chain
© Morecraft Drury 2014

## Slide 29: Engineering Services Commissioning
The PM is to ensure that the commissioning of the separate systems are properly planned and executed, so that the system works as a whole at practical completion/handover
Commissioning should be started as early as possible
Employ a separate commissioning contractor
Implement procedures for ongoing commissioning during defects period
Ensure O&M manuals complete
© Morecraft Drury 2014

## Slide 30: Completion & Handover
Ensure contract administrator has inspected the works and issued PC certificate with list of outstanding snags
Ensure client has insurances and security in place
Final account
Ensure owner/ tenant fit out works are programmed, co-ordinated and have access
Ensure client has commissioning in place during occupancy
Liaise with in-house management on moving in staff
© Morecraft Drury 2014

## Slide 31: Where Could It Possibly Go Wrong?
The Project Manager sits at the top of the project hierarchy and the buck stops with him when it all goes wrong . Whether he has been negligent or in breach of contract or whether he has in some way contributed to a problem due to his action or inaction on a matter that was within another consultants appointment. PM’s are frequently being brought in for contribution by other consultants who are defendants in an action
© Morecraft Drury 2014

## Slide 32: Where Could It Possibly Go Wrong?
Examples
  Breach of planning consent – demolition of existing structures in breach of planning consent in order to bring about a “new build” scheme which would save the VAT that a refurbishment scheme would add to its costs. The PM was trying to go the extra mile for the client but then ended up instructing a demolition that it thought it could retrospectively obtain permission for.
  The reality was that the planning authority would not grant planning and the scheme was left with no where to go as it was clearly impossible to undo the demolition
  The PM was (in my opinion) negligent although his actions were in an effort to increase the client’s profits.
© Morecraft Drury 2014

## Slide 33: Where could it possibly go wrong?
Example
  Delay and associated loss and expense claim caused by a failure of a geotechnical engineer to make appropriate arrangements for the remediation of contaminated soil. PM brought in for contribution for his part in failing to secure a “home” for the contaminated material on an adjacent site.
  Although main liability with engineer, failure to ensure the Project Execution Plan had been issued setting out the communication strategy, poor advice of the extent and quantum of delays etc left PM exposed to potential small contribution due to the confused nature of communication and clarity on roles and responsibilities .
© Morecraft Drury 2014

## Slide 34
Example
  PM failed to ensure that a design and build contractor had adequate professional indemnity insurance. A dome on the building collapsed due to design defects.
  It was found that PM had a duty of care to ensure that adequate insurance was in place . If the PM did not have the expertise in this field he should have sought expert advice
© Morecraft Drury 2014

## Slide 35
Example
  PM employed to manage the construction of a new factory. A fire destroyed the factory very quickly and the PM’s were sued for failing to advise on the combustible nature of the insulation used.
  The PM’s were found to be in breach of a duty of care to advise the client of the risk, even though the client would not have acted upon the advice. The PM’s appointment included specifying materials
© Morecraft Drury 2014

## Slide 36: What could possibly go wrong?
Example
  PM’s appointed to design and install restaurant kitchen equipment. There was a problem with the spit roaster after opening of the restaurant and there was a fire. The PM’s had a duty to check that the equipment was fire proof and that the manufacturers recommendations were followed.
  The PM sent a letter received from the manufacturer to the client which was ignored but the PM’s were considered on appeal to be liable as they should have been more proactive in assessing the fire risk than merely sending on the manufacturers letter.
© Morecraft Drury 2014

## Slide 37: Further Areas for Consideration
Ensuring proper commissioning of M&E services with test certificates
Arguments between client or tenant and project manager whether Practical Completion properly achieved i.e. Still too many items of outstanding work or commissioning
Over certification of monies due to a contractor or failure to deduct the value of works not in accordance with the specification . An issue if the contractor becomes insolvent
Failing to properly report on the effects of delays
© Morecraft Drury 2014

## Slide 38: Further Areas for Consideration
Failure to properly programme and manage the design phase
Failure to ensure performance bonds and warranties in place from sub-contractors with design liabilities
With effect from 1st May 2009 the RICS New Rules of Measurement came into force which introduced a clear framework which facilitates a systematic approach to compiling cost estimates and cost plans. It requires that risk management uses specific risk allowances for each risk and not a standard percentage across the board. Failure to use these new rules may leave the QS and PM negligent if costs are not properly controlled
© Morecraft Drury 2014

## Slide 39: THANK YOU
TREVOR DRURY
MBA, PG Dip Project Management, PG Dip Law, FRICS, CIOB, MCIArb
Managing Director
Morecraft Drury
0117 313 1515 or 020 7769 6781
07760 294 201
trevor.drury@morecraft-drury.com
www.morecroft-drury.com
Castlemead, Lower Castle Street, Bristol, BS1 3AG
Central Court, 25 Southampton Buildings, London WC2A 1AL
© Morecraft Drury 2014