## Slide 1: THE CONSTRUCTION ACT AND ADJUDICATION – AVOIDING THE PITFALLS Trevor Drury Managing Director Morecraft Drury 020 7769 6781 trevor.drury@morecraft-drury.com

## Slide 2: THE CONSTRUCTION ACT and ADJUDICATION AVOIDING THE PITFALLS
How to avoid some of the traps that could result in you being party to an adjudication
If you are considering launching an adjudication, or having to defend one, here are some of the pitfalls to avoid

## Slide 3: THE CONSTRUCTION ACT and ADJUDICATION AVOIDING THE PITFALLS
Payment
Since the introduction of the Housing, Grants, Construction & Regeneration Act 1996 it has been a requirement for notices to be given by the payer of the amount due to the payee within 5 days of the payment due date.
The changes brought about by the Local Democracy, Economic Development and Construction Act 2009 which came into effect in England and Wales in October 2011 has created some challenges!

## Slide 4: THE CONSTRUCTION ACT and ADJUDICATION AVOIDING THE PITFALLS
Payments
  s109 Entitlement to instalments or stage payments
  Parties are free to agree the amounts of payments and the intervals or circumstances in which they become due
  In the absence of such agreement the relevant provisions of the Scheme for Construction Contracts applies

## Slide 5: THE CONSTRUCTION ACT and ADJUDICATION AVOIDING THE PITFALLS
Payments
  s110 states that every construction contract shall provide an adequate mechanism for determining what payments become due and when
  Must provide for a final date for payment
  s110A requires the payer or specified person to give a notice to the payee not later than 5 days after the payment due date ( contract can also require the payee to give a notice)

## Slide 6: THE CONSTRUCTION ACT and ADJUDICATION AVOIDING THE PITFALLS
Notices
  A compliant payment notice must specify the sum due or to have been due at the payment due date and the basis on which it has been calculated
  A payment notice must be given even if the payment is assessed to be zero
  If the payer fails to issue a payment notice within 5 days of the due date, the payee may issue a notice under s110B
  If an application for payment has already been issued as required by the contract, before the payer’s notice or payment certificate has been issued, there is no need to issue another notice.

## Slide 7: THE CONSTRUCTION ACT and ADJUDICATION AVOIDING THE PITFALLS
Payment
  JCT, NEC and other standard forms of contract and their related subcontracts set out the payment terms and what notices are required to comply with the HGCRA
  Failure to comply with those requirements exposes the defaulting party to the risk of adjudication proceedings
  It is obviously preferable that the contract is agreed before work commences so that there is no dispute concerning the payment terms
  Where a contract has not been agreed and the payment terms have not been agreed, and the parties have not complied with the requirements of the HGCRA, the Scheme for Construction Contracts will be implied into the contract

## Slide 8: THE CONSTRUCTION ACT and ADJUDICATION AVOIDING THE PITFALLS
Payless notices
  s111 (3) payer’s notice of intention to pay less than the notified sum
  Must specify the sum that the payer considers to be due on the date the notice is served
  Must state the basis on which the sum is calculated
  Must be given not later than the prescribed period before the final date for payment. JCT is not later than 5 days and the default position under the Scheme is 7 days

## Slide 9: THE CONSTRUCTION ACT and ADJUDICATION AVOIDING THE PITFALLS
Failure to issue payment/payless notice – Interim Payments
The advent of the “smash and grab” adjudication
  ISG v Seevic College
  no payment notice or payless notice
  Adjudicator awarded circa £1.1m in favour of ISG, the amount claimed by ISG
  The judge awarded summary judgement for ISG
  “if the employer fails to serve any notices in time it must be taken to be agreeing the value stated in the application, right or wrong.”

## Slide 10: THE CONSTRUCTION ACT and ADJUDICATION AVOIDING THE PITFALLS
Failure to issue Payment/payless notices
  Galliford Try v Estura
  Concerned IA 60 "Indicative Final Account and Valuation Summary“ for £12.66m, £5m greater than the contract sum
  No payment or payless notice given
  Galliford’s application was for circa £4m and the adjudicator awarded in full
  At summary judgement the judge, due to Estura’s inability to pay £4m, and that this was near the final account, considered that there would be no incentive on GT to complete the works and submit a final account. He awarded a stay of part of the amount and awarded £1.5m

## Slide 11: THE CONSTRUCTION ACT and ADJUDICATION AVOIDING THE PITFALLS
Failure to issue payment/payless notice – Final accounts
  Harding v Paice
  Failure to issue a compliant payless notice in that it did not set out the basis of calculation
  Adjudicator awarded the contractor £398K plus VAT (3rd adjudication)
  Paice issued another 4th adjudication for the proper valuation of the final account.
  Harding sought an injunction to stop 4th adjudication
  Judge dismissed application for injunction as the JCT IFC required payment of the “amount properly due to the contractor” but payment to be made of the decision in adjudication no.3

## Slide 12: THE CONSTRUCTION ACT and ADJUDICATION AVOIDING THE PITFALLS
The timing of Applications for Payment
  Leeds City Council v Waco
  There are dates stipulated in the contract when applications for interim payment should be submitted
  Applications for payment will not be permitted outside of those dates
  In the above case applications for payment were issued too early
  There was a course of dealing where applications for payment were accepted 3-5 days late but not early!
  The message here is make sure you comply with the contract dates for submitting applications for interim payment

## Slide 13: THE CONSTRUCTION ACT and ADJUDICATION AVOIDING THE PITFALLS
The Timing of Applications for payment
  This was also an issue in Henia v Beck as the application was issued 6 days late for April but did not qualify as an early May application.
  The CA issued an interim payment certificate
  The Employer issued a payless notice valuing the certificate at zero for its claim for LD’s which the judge considered valid
  The fact that the CA had not provided a decision on an EOT did not prevent the Employer deducting LDs

## Slide 14: THE CONSTRUCTION ACT and ADJUDICATION AVOIDING THE PITFALLS
Payment Notices – Lessons learned
  Ensure that you or the specified person issue the notice.
  Applications for interim payment must be unambiguous and communicate that it is an interim application, the due date it refers to, and set out the notified sum
  Issue within the time stipulated in the contract or Scheme
  Ensure that the notice sets out the basis of calculation

## Slide 15: THE CONSTRUCTION ACT and ADJUDICATION AVOIDING THE PITFALLS
  If you are the payee and an application for payment has not already been issued, make sure you issue a s110B notice
  Ensure any payless notice is issued within time and again sets out the basis of calculation
  The courts will treat interim applications differently to final accounts (Kilker Projects Ltd v Purton[2016] (14 October)
  An Employer can challenge a CA certificate by issuing a payless notice

## Slide 16: THE CONSTRUCTION ACT and ADJUDICATION AVOIDING THE PITFALLS
Payment Schedules – be careful!
  Due to the complex provisions of the HGCRA contracts, the parties often include a payment schedule setting out dates for submission of applications for payment, due dates, date for the issue of the payment notice, payless notice and final date for payment.
  This is good if it aids communication however; ensure that the schedule allows for project overruns ( Grove Developments v Balfour Beatty)
  Ensure that the correct dates are set out in the schedule. The courts will correct any obvious errors where there has been a departure from the regular monthly cycle ( Bouygues v Febrey Structures)

## Slide 17: THE CONSTRUCTION ACT and ADJUDICATION AVOIDING THE PITFALLS
Suspension – s112
  At least 7 days notice must be given of the intention to suspend performance stating the ground or grounds for suspension
  The right to suspend ceases on payment in full of the amount due
  Ensure that the notice is not given prematurely and that the formalities required for the notice are complied with
  Failure to do so could result in a repudiatory breach of contract

## Slide 18: THE CONSTRUCTION ACT and ADJUDICATION AVOIDING THE PITFALLS
Settlement Agreements
  Separate agreement or a variation of the terms of the contract?
  Is it a construction contract in accordance with the HGCRA?
  J Murphy & Sons v W Mayer & Sons
  The adjudication clauses in the sub-subcontract were considered broad enough to cover a dispute arising under the settlement agreement
  The judge did however state that he would be sympathetic to an application for permission to appeal on the basis it would be helpful for an appellate decision on this important area.

## Slide 19: THE CONSTRUCTION ACT and ADJUDICATION AVOIDING THE PITFALLS
If contemplating an adjudication the following points should be considered:
  Ensure that it is a construction contract within the meaning of the HGCRA and not excluded by those activities stated in s105 (2) which mainly concern mining, oil, gas and steelwork to provide access on power stations, water treatment and bulk storage of chemicals, oil, gas etc.
  Residential occupiers , unless their contract expressly provides for adjudication

## Slide 20: THE CONSTRUCTION ACT and ADJUDICATION AVOIDING THE PITFALLS
Further points to be considered
  Disputes under more than one contract
    It may be that part of the dispute does not arise under the contract
    If there are 2 disputes, they cannot be referred to the same adjudication without permission of the responding party
  Ensure that the correct nominating body is used
  An adjudicator has to be appointed within 5 days and it is the referring party’s responsibility to ensure that he is appointed in time

## Slide 21: THE CONSTRUCTION ACT and ADJUDICATION AVOIDING THE PITFALLS
Further points to be considered
  The referral notice must be served in writing to the adjudicator and the responding party, copy of the relevant parts of the contract and other documents relied upon
  An adjudicator may, with the consent of both parties adjudicate more than one dispute under the same contract
  The adjudicator may, with the parties consent, adjudicate at the same time, related disputes under different contracts

## Slide 22: THE CONSTRUCTION ACT and ADJUDICATION AVOIDING THE PITFALLS
Jurisdiction
  The adjudicator’s jurisdiction to decide the dispute referred to him is often challenged by the responding party to prevent subsequent enforcement. If you are going to participate in an adjudication you must reserve your rights regarding any jurisdictional challenge, and repeat it at each subsequent submission. Potential reasons for a challenge:
  Not a “construction contract” as defined in the HGCRA
  Not a party
  Dispute has not crystallised
  More than one dispute referred
  Dispute does not arise under the contract

## Slide 23: THE CONSTRUCTION ACT and ADJUDICATION AVOIDING THE PITFALLS
  Dispute is under multiple contracts or a side agreement
  Dispute decided in a previous adjudication
  Errors in the appointment of the adjudicator
  Late service of referral
  Late decision
  Answering the wrong question

## Slide 24: Thank You
Trevor Drury
MBA, PG Dip Bar, PG Dip Law, PG Dip Project Management, FRICS, FCIOB, MCIArb
Managing Director
Morecraft Drury
trevor.drury@morecraft-drury.com
Castlemead, Lower Castle Street, Bristol BS1 3AG
0117 313 1515
Central Court, 25 Southampton Buildings, London WC2A 1AL
020 7769 6781